## Đề-2-Ascent
Cột 1 | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header | 2025-06-20 | 2025-06-21 | 90% | Cường |  | 2020-12-14 | 95% | Cường | đã reponsive chưa thêm animation
Logo | 2025-06-21 | 2025-06-22 | 50% | Cường |  | 2020-12-14 | 50% | Cường | đã reponsive chưa thêm animation
Navbar | 2025-06-22 | 2025-06-23 | 90% | Cường |  | 2020-12-14 | 90% | Cường | đã reponsive chưa thêm animation
Submenu | 2025-06-23 | 2025-06-24 | 100% | Cường |  | 2020-12-14 | 100% | Cường | đã reponsive chưa thêm animation
Search form | 2025-06-24 | 2025-06-25 | 90% | Cường |  | 2020-12-14 | 90% | Cường | đã reponsive chưa thêm animation
Login popup | 2025-06-25 | 2025-06-26 | 80% | Cường |  | 2020-12-14 | 80% | Cường | đã reponsive chưa thêm animation
Footer | 2025-06-26 | 2025-06-27 | 100% | Đăng |  | 2020-12-14 | 100% | Đăng
Elementary | 2025-06-26 | 2025-06-28 | 90% | Cường |  |  | 100% | Cường | đã reponsive chưa thêm animation
Number talks | 2025-06-28 | 2025-06-29 | 90% | Cường |  |  | 100% | Cường | đã reponsive chưa thêm animation
About Us | 2025-06-29 | 2025-06-30 | 90% | Cường |  |  | 100% | Cường | đã reponsive chưa thêm animation
Programs | 2025-06-30 | 2025-07-01 | 90% | Cường |  |  | 100% | Cường | đã reponsive chưa thêm animation
Portfolio | 2025-07-01 | 2025-07-02 | 90% | Cường |  |  | 100% | Cường | đã reponsive chưa thêm animation
Service | 2025-07-02 | 2025-07-03 | 90% | Cường |  |  | 100% | Cường | đã reponsive chưa thêm animation
get connected | 2025-06-20 | 2025-06-22 | 90% | Đăng |  |  | 100% | Đăng | chưa animation
blog | 2025-06-23 | 2025-06-25 | 100% | Đăng |  |  | 100% | Đăng | chưa animation
testimonial | 2025-06-27 | 2025-06-28 | 95% | Đăng |  |  | 100% | Đăng | chưa backgrund chưa animation
professtional | 2025-06-28 | 2025-06-29 | 100% | Đăng |  |  | 100% | Đăng | chưa animation
ffaq | 2025-06-30 | 2025-07-02 | 100% | Đăng |  |  | 100% | Đăng | chưa style giống chưa animation
student knowledge | 2025-07-03 | 2025-07-05 | 80% | Đăng |  |  |  | Đăng | chưa animation, chưa đúng layout